## Sheet1
This document shows the steps and deadlines for a homeschool convention / SCC year (January 1 - December 31). Please bear with us as we modify as necessary.
WHO | ACTION | TIME FRAME
Sonlight | Apply for conventions based on sales & feedback from the previous year | ASAP
Sonlight | Decide which events SL will sponsor and post to the SCC intranet | November
Sonlight | Post new SCC Agreement, Returning SCC Application, Event Application, Assistant Profiles, and other forms to intranet | November
SCC | SCCs wanting to return the following year, fill out the returning SCC application | November 30th
SCC | Complete Event Application and send to Sonlight | due to Sonlight December 15th
Sonlight | Inform SCCs if approved for events they applied for | Mid December
Sonlight | Post a list of events we don't have an SCC for yet | November and ongoing
SCC | Sign and return SCC Agreement to Sonlight | Submit with Application
SCC | Send lists of personal contacts (prospects) to Sonlight | First business day of each month if you have any contacts
Sonlight | Send copies of convention paperwork to SCC | When Sonlight registers and/or SCC is approved
SCC | Send in Assistant Profiles | 2 Months before individual convention
SCC | Request any special samples needed from SL. We cannot guarantee every request, but will try to help where feasible | January
Sonlight | Send catalogs, postcards, samples, banners, $10 GC and other booth material | anywhere from February to 3 weeks before event
Sonlight | SL sends expense check once you send all assistant profiles | 2 weeks before the convention and only once all assistant profiles are received at SL
SCC | Request pre-registration check from SL | see procedure called "Pre Registration Procedures for SCCs.doc"
SCC | Submit pre-registration form and check to convention, noting booth of choice | at convention
SCC | Fill out convention evaluation | at convention
SCC | Submit prospect list & PEQ to Sonlight | within 5 business days of the convention if either are late list will not be backdated.
Sonlight | Pay draw to SCC if requested | Once prospect list and PEQ are received
Sonlight | Pay commissions | January, April, July & October